## Daily Activits
DAILY | ACTIVITIES FOR RESONANCE PATH
DATE | START TIME | EDN TIME | Hours | EVENT
Jun 23 2017 |  | 7 hours | 7:00 | Developed the first version of KairoScope
Jun 24 2017 |  | 10 hours | 10:00 | Developed the first version of KairoScope
Jun 25 2017 |  | 10 hours | 10:00 | Developed the first version of KairoScope
Jun 26 2017 |  | 8 hours | 8:00 | Developed the first version of KairoScope
Jun 27 2017 |  | 5 hours | 5:00 | Developed the first version of KairoScope
Jun 28 2017 |  | 3 hours | 3:00 | Developed the first version of KairoScope
July 1 2017 | 15:00 | 16:45 | 1:45 | Meeting and designed new database struction
| 20:40 | 23:50 | 3:10 | Set up AWS and EC2 server
July 2 2017 | 10:20 | 12:20 | 2:00 | Testing server and database
| 23:00 | 1:00 | 2:00 | Wrote some code for transfor data
July 3 2017 | 10:40 | 13:15 | 2:35 | Transfored data from FieldBook to AWS EC2 (MongoDB)
| 21:00 | 22:30 | 1:30 | Connecting old code to new backend code and implenmented Login function
July 4 2017 | 10:30 | 12:15 | 1:45 | Transfored AddReading to new server and debug
| 13:30 | 17:12 | 3:42 | Debug and solved the authentication problem
| 21:20 | 22:15 | 0:55 | Changed the code for Reading page
July 5 2017 | 10:30 | 13:40 | 3:10 | Made HexagramImage code, changed code to non SSL version in order to fit different browers
| 14:20 | 19:00 | 4:40 | Transfored Reading page code completely
| 21:00 | 22:36 | 1:36 | Transfored Delete Reading function
July 6 2017 | 10:30 | 12:00 | 1:30 | Worded on Add Journal code
| 13:37 | 17:00 | 3:23 | Finished Add Journal and Delete Journal functions
| 18:05 | 20:30 | 2:25 | Finished Update Journal function
| 21:15 | 1:11 | 3:00 | Finished Hexagram search function
July 7 2017 | 10:36 | 12:00 | 1:24 | Changed get recent readings and set GitHug
| 13:10 | 19:37 | 6:27 | Finished Reading search and tested
July 8 2017 | 11:00 | 12:32 | 1:32 | Wrote code to match line 13 25 46 bigram ids to Hexagram collections
July 10 2017 | 0:30 | 25:05 | 24:35 | Made some changes for menu, put logo and background image on the first page
| 11:20 | 13:00 | 1:40 | Made some changes for texts and designed new coin choose function
| 14:30 | 16:20 | 1:50 | Finished the coin choose function
July 13 2017 | 11:00 | 12:30 | 1:30 | Meeting with Joe and changed choose coin function
July 14 2017 | 10:50 | 13:00 | 2:10 | Started to add Hexagram changing function
| 13:40 | 17:20 | 3:40 | Finished Hexagram changing function
| 21:30 | 1:50 | 3:20 | Set up new LightSail server and transfored code and data to the new server
July 15 2017 | 11:00 | 12:50 | 1:50 | Changed Hexagram update form and made this new daily activities table
| 14:09 | 16:15 | 2:06 | Redesigned AddJournal function
| 23:20 | 24:25 | 1:05 | Changed code for Add Journal function
July 16 2017 | 12:04 | 17:30 | 5:26 | Contiune working on Add Journal function
July 17 2017 | 12:15 | 13:30 | 1:15 | Contiune working on Add Journal function
| 16:40 | 18:13 | 1:33 | Contiune working on Add Journal function
| 19:13 | 19:30 | 0:17 | Contiune working on Add Journal function
| 19:45 | 20:46 | 1:01 | Finished Add Journal functions
July 19 2017 | 17:00 | 19:40 | 2:40 | Working on update Journal function
| 22:26 | 23:10 | 0:44 | Working on update Journal function
July 20 2017 | 0:10 | 1:17 | 1:07 | Working on update Journal function
| 11:50 | 13:30 | 1:40 | Working on update Journal function
| 15:02 | 16:20 | 1:18 | Working on update Journal function
| 18:08 | 19:30 | 1:22 | Working on update Journal function
| 22:00 | 23:59 | 1:59 | Finished update Journal function and debug
July 21 2017 | 0:00 | 0:27 | 0:27 | Finished delete Journal function
| 11:00 | 12:00 | 1:00 | Working on register page
| 14:02 | 17:30 | 3:28 | Working on register page
July 22 2017 | 11:05 | 12:38 | 1:33 | Finished register user page
| 13:30 | 14:50 | 1:20 | Fixed some bugs
July 28 2017 | 10:00 | 17:00 | 7:00 | Changed PingPongState to relate to readings
| 22:10 | 24:00 | 1:50 | Fixed some bugs
| 0:00 | 1:20 | 1:20 | Fixed some bugs
| 10:29 | 11:45 | 1:16 | Working on showing journal page
| 22:12 | 23:01 | 0:49 | Finised revising showing journal page
August 1 2017 | 22:38 | 22:52 | 0:14 | Redesigned appliciation's architecture
August 3 2017 | 14:20 | 19:00 | 4:40 | Changed journal can be unattached to any reading
August 9 2017 | 12:00 | 14:20 | 2:20 | Fixed some bugs
September 22 2017 | 15:20 | 18:30 | 3:10 | Meeting and add new feature about multiple roles for users. Changing some display texts.
October 2 2017 | 15:30 | 16:10 | 0:40 | Making some changes for new requirements.
| 20:30 | 21:50 | 1:20 | Changing Bootstrap to V4.0 beta
October 5 2017 | 18:35 | 19:30 | 0:55 | Restructure Node files
| 20:30 | 21:10 | 0:40 | Moving username password login and checkExsitUser function to UserActions
October 6 2017 | 14:45 | 18:15 | 3:30 | Restructuring whole architecture. Changing login and setup to use Bcrypt library, using JsonWebToken instead of cookie for authentication, adding the checking authentication component to Reading page, and switching reading page to using back-end verification for users' role.
October 7 2017 | 13:00 | 18:20 | 5:20 | Changing reading and all search page code to the new structure
October 8 2017 | 11:00 | 14:10 | 3:10 | Changing Journal list function to the new structure. Trying to find a JS standard for linter.
| 15:02 | 18:41 | 3:39 | Configuring Eslint for the project and restructuring Journal list and Unattached journal list function.
October 9 2017 | 10:05 | 12:30 | 2:25 | Restructuring and finding a code style for the project.
| 14:00 | 16:50 | 2:50 | Trying to config and implement Airbnb style for the code standard for the project.
October 10 2017 | 11:30 | 15:21 | 3:51 | Restructuring DetailedReading function.
| 18:00 | 18:36 | 0:36 | Changing Navbar
| 20:10 | 21:17 | 1:07 | Trying to integrate Facebook login.
October 11 2017 | 10:50 | 13:23 | 2:33 | Integrating Facebook login.
| 15:20 | 17:50 | 2:30 | Finishing login function and clearing some code.
October 12 2017 | 10:16 | 11:05 | 0:49 | Refactoring AddReadingContainer code.
| 16:30 | 18:50 | 2:20 | Trying to make add reading function to use the Modal that comes from Bootstrap.
October 13 2017 | 14:30 | 17:34 | 3:04 | Changing the Add Reading function to the new structure and using a interface.
October 14 2017 | 17:00 | 17:20 | 0:20 | Refactoring delete reading function.
| 18:57 | 19:20 | 0:23 | Refactoring delete reading function.
| 20:30 | 22:45 | 2:15 | Refactoring delete reading function.
October 17 2017 | 10:59 | 13:12 | 2:13 | Restructuring Journal relative code.
| 14:08 | 15:30 | 1:22 | Restructuring Journal relative code.
| 16:10 | 18:53 | 2:43 | Restructuring Journal relative code.
| 20:17 | 21:30 | 1:13 | Restructuring Journal relative code.
October 18 2017 | 10:50 | 13:12 | 2:22 | Restructuring Update journal function.
| 16:40 | 18:20 | 1:40 | Refactoring journal related code.
| 21:10 | 22:40 | 1:30 | Refactoring journal related code.
October 19 2017 | 11:30 | 12:00 | 0:30 | Integrating jQuery ui's datepicker to AddReading, AddJournal, and SearchReadings function.
| 4:30 | 6:00 | 1:30 | Integrating jQuery ui's datepicker to AddReading, AddJournal, and SearchReadings function.
| 20:00 | 21:38 | 1:38 | Integrating jQuery ui's datepicker to AddReading, AddJournal, and SearchReadings function.
October 20 2017 | 15:00 | 18:30 | 3:30 | Refactoring code for Hexagram editing.
October 22 2017 | 18:34 | 19:00 | 0:26 | Refactoring code for Hexagram editing.
| 21:07 | 21:30 | 0:23 | Refactoring code for Hexagram editing.
October 23 2017 | 13:30 | 14:10 | 0:40 | Refactoring code for Hexagram editing.
| 16:12 | 19:12 | 3:00 | Integrating Google Login.
| 20:30 | 22:48 | 2:18 | Integrating Google Login.
October 24 2017 | 10:15 | 12:15 | 2:00 | Putting new version App to the productive server.
October 25 2017 | 15:50 | 16:20 | 0:30 | Changing the PingPong states for the journal page.
| 20:10 | 22:40 | 2:30 | Refactoring code. (Moving out the click, submit, and other callback function to class in order to improve the performance.)
October 26 2017 | 10:32 | 11:30 | 0:58 | Refactoring code and debuging.
October 27 2017 | 12:30 | 13:40 | 1:10 | Adding picking Hexagram line function in add reading page.
| 14:29 | 19:10 | 4:41 | Adding picking Hexagram line function in add reading page.
| 20:40 | 21:20 | 0:40 | Adding picking Hexagram line function in add reading page.
October 28 2017 | 10:41 | 11:35 | 0:54 | Starting to add Settings function.
| 16:00 | 18:30 | 2:30 | Working on adding settings function.
| 21:20 | 23:00 | 1:40 | Finishing user settings function.
October 29 2017 | 14:10 | 16:00 | 1:50 | Adding winston library to node file and refactoring code for MongoDB file.
| 21:00 | 22:21 | 1:21 | Adding winston library to node file and refactoring code for MongoDB file.
October 30 2017 | 18:10 | 18:40 | 0:30 | Meeting and revising some content.
| 20:30 | 21:27 | 0:57 | Starting to add show all reading in the add reading page.
October 31 2017 | 14:00 | 14:30 | 0:30 | Working on show all list of reading function.
| 16:00 | 16:40 | 0:40 | Working on show all list of reading function.
| 19:35 | 22:47 | 3:12 | Working on show all list for add reading function.
November 01 2017 | 12:51 | 14:00 | 1:09 | Finishing show all list for add reading function.
| 15:30 | 19:00 | 3:30 | Trying to build a test structure for the project.
| 19:38 | 21:00 | 1:22 | Trying to build a test structure for the project.
November 02 2017 | 14:50 | 15:50 | 1:00 | Testing Actions.
| 16:30 | 17:30 | 1:00 | Testing Actions.
| 19:31 | 21:07 | 1:36 | Testing Actions.
November 03 2017 | 14:00 | 18:00 | 4:00 | Testing Actions.
| 19:34 | 22:10 | 2:36 | Testing Actions.
November 04 2017 | 18:40 | 19:33 | 0:53 | Testing Actions.
| 21:00 | 22:16 | 1:16 | Fixing a bug in ImageDescription component and clearing some unuseful files.
November 05 2017 | 11:32 | 12:10 | 0:38 | Testing Util file.
| 13:00 | 14:26 | 1:26 | Testing Util file.
November 07 2017 | 11:10 | 12:30 | 1:20 | Updating React js to current version 16.
| 16:36 | 17:35 | 0:59 | Trying to start testing React components.
| 19:46 | 22:15 | 2:29 | Trying to start testing React components.
November 10 2017 | 11:20 | 12:00 | 0:40 | Starting to design sharing function
| 15:10 | 17:00 | 1:50 | Starting to design sharing function and fixing a bug for journal form component. (cancel will keep the journal's state)
November 11 2017 | 15:55 | 16:20 | 0:25 | Working on the sharing function.
| 17:30 | 18:20 | 0:50 | Working on the sharing function.
November 12 2017 | 13:37 | 14:32 | 0:55 | Working on the sharing function.
| 14:41 | 15:30 | 0:49 | Working on the sharing function.
November 14 2017 | 10:20 | 11:00 | 0:40 | Working on the sharing function.
| 12:17 | 12:30 | 0:13 | Working on the sharing function.
| 17:07 | 18:35 | 1:28 | Working on the sharing function.
| 19:57 | 20:30 | 0:33 | Working on the sharing function.
November 15 2017 | 12:00 | 12:30 | 0:30 | Working on the sharing function.
| 14:30 | 15:11 | 0:41 | Working on the sharing function.
| 17:00 | 18:01 | 1:01 | Working on the sharing function.
November 16 2017 | 14:28 | 15:00 | 0:32 | Working on the sharing function.
| 16:34 | 17:09 | 0:35 | Working on the sharing function.
| 20:01 | 20:38 | 0:37 | Working on the sharing function.
November 17 2017 | 10:41 | 12:11 | 1:30 | Working on the sharing function.
| 16:17 | 18:10 | 1:53 | Working on the sharing function.
November 18 2017 | 12:20 | 12:47 | 0:27 | Working on the shwoing shared readings function.
| 14:02 | 15:24 | 1:22 | Working on the shwoing shared readings function.
November 19 2017 | 12:23 | 12:50 | 0:27 | Working on the shwoing shared readings function.
| 16:20 | 18:12 | 1:52 | Working on the shwoing shared readings function.
| 20:35 | 21:09 | 0:34 | Finshing the sharing function.
November 20 2017 | 11:19 | 13:26 | 2:07 | Strating to organize css.
| 19:20 | 20:00 | 0:40 | Organizing css.
November 21 2017 | 20:56 | 21:33 | 0:37 | Organizing css.
November 22 2017 | 12:12 | 12:51 | 0:39 | Organizing css.
| 16:49 | 17:12 | 0:23 | Organizing css.
| 17:26 | 18:02 | 0:36 | Organizing css.
| 19:35 | 20:09 | 0:34 | Organizing css.
November 23 2017 | 11:18 | 12:51 | 1:33 | Organizing css.
| 14:00 | 16:49 | 2:49 | Organizing css.
November 25 2017 | 14:20 | 18:00 | 3:40 | Changing the isShared to isPrivate for the Journal form and also fixing a missing class of avater-photo in css file.
| 20:00 | 21:24 | 1:24 | Finding out the issue of reloading the page when a user click a Link component is caused by a Chrome's extension.
November 26 2017 | 15:41 | 16:00 | 0:19 | Setting up the react-hot-loader for the project.
| 17:00 | 18:34 | 1:34 | Making RecentReadings page to use the redux's state first.
| 21:30 | 22:36 | 1:06 | Making RecentReadings page to use the redux's state first.
November 27 2017 | 20:00 | 22:20 | 2:20 | Making RecentReadings page to use the redux's state first.
November 27 2017 | 14:49 | 16:50 | 2:01 | Changing some display texts and fixing some bug for addReading function.
| 17:24 | 18:41 | 1:17 | Making a database backup plan. Creating some indexs for the database.
| 22:10 | 23:59 | 1:49 | Trying to setup ssl for the website.
November 28 2017 | 0:01 | 0:15 | 0:14 | Trying to setup ssl for the website.
| 11:22 | 12:32 | 1:10 | Setting up SSL for the website.
| 18:55 | 22:00 | 3:05 | Trying to sovle the huge increasement of bundle size after use React-hot-loader. (Not solve yet)
November 30 2017 | 13:00 | 14:00 | 1:00 | Debuging and fixing some bugs.
| 20:10 | 21:47 | 1:37 | Fixing a bug of updating a journal will erase same journals' shareList in different readings.
December 01 2017 | 12:03 | 12:56 | 0:53 | Adding the function of showing all journal.
| 20:05 | 21:03 | 0:58 | Adding the function of showing all journal.
December 02 2017 | 11:40 | 12:50 | 1:10 | Adding the function of showing all journal.
| 15:38 | 18:22 | 2:44 | Finishing the function of showing all journal.
December 03 2017 | 11:00 | 12:00 | 1:00 | Researching service worker.
| 15:00 | 16:35 | 1:35 | Starting to implement a service worker for the App.
| 20:17 | 21:17 | 1:00 | Adding a service worker for the App.
December 04 2017 | 16:12 | 17:38 | 1:26 | Changing the cache stratety and improve the PWA ability.
December 05 2017 | 15:43 | 16:10 | 0:27 | Doing some PWA research.
December 07 2017 | 20:10 | 21:34 | 1:24 | Strating to implement push notification function.
December 08 2017 | 11:50 | 12:40 | 0:50 | Working on push notification feature.
| 16:00 | 17:30 | 1:30 | Working on push notification feature.
| 20:17 | 22:04 | 1:47 | Working on push notification feature.
December 09 2017 | 10:39 | 11:50 | 1:11 | Working on push notification feature.
| 12:36 | 13:14 | 0:38 | Working on push notification feature.
| 19:01 | 20:33 | 1:32 | Working on push notification feature.
December 10 2017 | 10:20 | 11:33 | 1:13 | Working on push notification feature.
| 14:40 | 17:10 | 2:30 | Working on push notification feature.
| 20:52 | 21:41 | 0:49 | Working on push notification feature.
December 11 2017 | 10:27 | 11:42 | 1:15 | Working on push notification feature.
| 16:15 | 18:46 | 2:31 | Working on push notification feature.
December 12 2017 | 17:56 | 18:10 | 0:14 | Changing some display texts for the journal content title list.
| 19:00 | 19:17 | 0:17 | Adding push notification to mutiple devices.
| 20:33 | 21:41 | 1:08 | Changing the FontAwesome library to V5. Doing some research for jsPdf library.
December 13 2017 | 11:07 | 12:30 | 1:23 | Working on output reading to PDF function.
| 20:10 | 21:50 | 1:40 | Working on output reading to PDF function.
December 14 2017 | 10:26 | 14:00 | 3:34 | Trying out html2canvas and jsPDF library. jsPDF is not suitable for our app.
| 19:38 | 23:35 | 3:57 | Working on PDF output function with pdfmake library. It seems like work for my case.
December 15 2017 | 13:13 | 13:44 | 0:31 | Working on PDF output function.
| 15:00 | 18:20 | 3:20 | Finishing PDF output function.
December 16 2017 | 10:00 | 12:10 | 2:10 | Doing the research of image hosting.
| 14:01 | 15:30 | 1:29 | Working on implementing upload images feature.
| 18:01 | 21:33 | 3:32 | Trying the Dropzone library with Cloudinary platform.
December 17 2017 | 20:33 | 22:17 | 1:44 | Implementing the upload image function.
December 18 2017 | 10:58 | 14:01 | 3:03 | Implementing the upload image function.
| 15:40 | 16:48 | 1:08 | Implementing the upload image function.
| 21:43 | 22:50 | 1:07 | Implementing the upload image function.
December 19 2017 | 12:30 | 14:41 | 2:11 | Finished upload image function and fixed a bug that relates to showing journals.
| 21:05 | 22:33 | 1:28 | Writing test code for ReadingActions and JournalActions.
December 20 2017 | 12:30 | 13:00 | 0:30 | Improving the test code for ReadingActions.
| 17:04 | 19:20 | 2:16 | Debug journal display code. (JournalForm component)
December 21 2017 | 17:35 | 18:10 | 0:35 | Designing the User Group function.
| 21:00 | 22:30 | 1:30 | Added ExtractTextPlugin for Webpack and fixed some configuration problems in webpack.config.js. Also, fixed some mistakes for service worker's cache strategy.
December 22 2017 | 16:40 | 17:20 | 0:40 | Implementing the user group functionality.
| 20:10 | 21:00 | 0:50 | Implementing the user group functionality.
December 23 2017 | 17:13 | 17:30 | 0:17 | Implementing the user group functionality.
| 20:27 | 21:19 | 0:52 | Implementing the user group functionality. (Optimized JWT message. Keeping minimum information in the JWT.)
December 24 2017 | 12:30 | 13:36 | 1:06 | Implementing the user group functionality.
| 14:33 | 16:52 | 2:19 | Implementing the user group functionality. Extracting UserPicker component from JournalSharingModal in order to reuse in UserGroup component.
December 25 2017 | 12:08 | 13:46 | 1:38 | Implementing the user group functionality.
| 15:38 | 16:01 | 0:23 | Implementing the user group functionality.
| 16:30 | 18:21 | 1:51 | Implementing the user group functionality.
| 19:50 | 20:18 | 0:28 | Implementing the user group functionality.
December 26 2017 | 13:27 | 16:19 | 2:52 | Finished the user group functionality.
January 2 2018 | 10:53 | 11:52 | 0:59 | Fixed a bug caused by changing JournalForm.js's inintialStates method to ret urn a promise, which causes this.somestates will not be initialed when children component mou nt
| 15:30 | 16:03 | 0:33 | Fixed a bug causes reading's userName to be null
| 16:04 | 16:46 | 0:42 | Debuging for Hexagram img_arr issue.
| 16:58 | 18:00 | 1:02 | Working on adding a custom name field for users.
January 3 2018 | 14:44 | 16:14 | 1:30 | Added a function that allows a user to customize its display name.
January 6 2018 | 13:18 | 14:00 | 0:42 | Adding a functionality of showing user id in UserPicker componeng.
| 20:09 | 20:18 | 0:09 | Changed custom name for some users.
January 10 2018 | 10:47 | 10:57 | 0:10 | Added Helmet to node js.
January 13 2018 | 16:30 | 17:58 | 1:28 | Update some outdated npm packages to date. Node's mongodb drive3.0 changed connection code. Html2canvas seems like has problem to update to alpha.9
| 20:32 | 22:07 | 1:35 | Doing some research for the Jest Snapshot test.
January 14 2018 | 14:25 | 17:04 | 2:39 | Doing some research for the unit test for components.
| 20:21 | 22:22 | 2:01 | Finished AddReadingForm component test. Fixed name spelling mistake for AddReadingJournalButton component and added a snapshot test for it.
January 15 2018 | 20:43 | 22:13 | 1:30 | Added a unit test and snapshot test for AddReadingJournalButton component.
January 16 2018 | 10:36 | 10:50 | 0:14 | Added a snapshot test for AlertPanel component.
| 19:30 | 21:49 | 2:19 | Added some test for components and had a meet with Spring to talk about some changing for the App.
January 17 2018 | 11:28 | 12:19 | 0:51 | Added an additional protection for update Hexagram function in the back-end code. Add test code for a component.
| 13:30 | 16:33 | 3:03 | Added test code for some components.
January 19 2018 | 17:46 | 18:26 | 0:40 | Add test code for ChooseHexagramLines component.
| 20:41 | 21:06 | 0:25 | Added test code for two components.
January 20 2018 | 11:23 | 12:03 | 0:40 | Added test for some components and also fixed a protential bug for ExstUserLoginForm component.
| 12:09 | 13:08 | 0:59 | Added test for components.
| 15:45 | 18:13 | 2:28 | Added test for components.
| 20:20 | 22:16 | 1:56 | Added test for components.
January 21 2018 | 11:19 | 13:53 | 2:34 | Added test code for JournalForm component. Also removed uneccessary async code from JournalForm Component.
| 14:40 | 15:58 | 1:18 | Finished test code for JournalForm component.
| 16:15 | 16:25 | 0:10 | Added more test code.
| 19:46 | 20:52 | 1:06 | Added test code for JournalList component.
January 22 2018 | 11:16 | 11:48 | 0:32 | Added more test code.
| 14:33 | 17:40 | 3:07 | Added more test code.
| 20:28 | 21:10 | 0:42 | Added more test code.
January 23 2018 | 10:51 | 12:20 | 1:29 | Added more test code for components.
| 15:40 | 17:30 | 1:50 | Added more test code for components.
| 20:42 | 22:05 | 1:23 | Added more test code for components.
January 24 2018 | 10:39 | 11:29 | 0:50 | Added more test code for two components.
| 13:09 | 13:20 | 0:11 | Added test code for SearchHexagramsForm component.
| 14:35 | 15:58 | 1:23 | Added more test code for components.
January 26 2018 | 22:00 | 22:30 | 0:30 | Added more test code for components.
January 29 2018 | 13:56 | 16:59 | 3:03 | Finished adding test code for components (Do not include container components).
| 17:39 | 18:20 | 0:41 | Desiging and assigning new features to different tasks.
January 30 2018 | 11:30 | 13:06 | 1:36 | Added five new fields for the Hexagram administration page.
| 14:26 | 18:20 | 3:54 | Changed interfaces to show the new format data. Added some temporary code in NormalRouters.js to add three associated hexagrams.
January 31 2018 | 11:00 | 12:43 | 1:43 | Added component to show associated hexagrams.
Febuary 3 2018 | 13:00 | 14:00 | 1:00 | Meeting with Spring to get new requirements and put them in the Github.
Febuary 4 2018 | 10:40 | 13:00 | 2:20 | Resolved #16
| 21:20 | 22:21 | 1:01 | Started to add HexagramContainerList component.
Febuary 5 2018 | 17:00 | 18:10 | 1:10 | Finised HexagramListContainer component.
| 20:00 | 21:38 | 1:38 | Fixed two bugs. Added test code for HexagramListContainer component.
Febuary 6 2018 | 10:49 | 12:31 | 1:42 | Added BigramSmallClock component as well as test code.
| 14:07 | 18:11 | 4:04 | Added BigramBlockSmall component as well as test code. Started to design detailed hexagram page.
| 20:19 | 22:02 | 1:43 | Working on hexagram detail page.
Febuary 7 2018 | 11:00 | 11:15 | 0:15 | Working on hexagram detail page.
| 14:10 | 16:11 | 2:01 | Finished hexagram detail page.
Febuary 9 2018 | 14:48 | 16:49 | 2:01 | Finished BigramClockBig component.
| 18:31 | 18:45 | 0:14 | Started making BigramBlockBig component.
| 20:36 | 22:51 | 2:15 | Working on BigramBlockBig component.
Febuary 10 2018 | 9:03 | 9:30 | 0:27 | Working on BigramBlockBig component.
| 13:00 | 13:30 | 0:30 | Working on BigramBlockBig component.
| 17:30 | 18:07 | 0:37 | Finished BigramClockBig component.
| 19:44 | 21:31 | 1:47 | Connected HexagramDetailModal with ReadingsContainer component.
Febuary 11 2018 | 12:20 | 13:10 | 0:50 | Refinement of the Hexagram Page.
| 16:00 | 17:18 | 1:18 | Improving poetry section in the hexagram detail page.
| 20:34 | 22:00 | 1:26 | Changed Navbar and started to add quartet bigrams to hexagram database.
Febuary 12 2018 | 16:30 | 18:22 | 1:52 | Adjust hexagram detail display page.
| 21:19 | 22:47 | 1:28 | Working on add Resonance Quartet Hexagrams.
Febuary 13 2018 | 10:25 | 11:43 | 1:18 | Finished adding resonance quartet hexagrams.
| 13:08 | 13:23 | 0:15 | Adjusted hexagram detail modal.
| 16:00 | 18:24 | 2:24 | Working on add line changing to hexagram.
| 20:22 | 22:00 | 1:38 | Working on add line changing to hexagram.
Febuary 14 2018 | 10:51 | 13:14 | 2:23 | Finished add line changing.
Febuary 15 2018 | 5:52 | 6:20 | 0:28 | Changed some display text.
Febuary 16 2018 | 11:42 | 12:30 | 0:48 | Working on automatically update Resonance code name in HexagramDetailModal componnet.
| 14:00 | 15:00 | 1:00 | Finished automatically update Resonance code name in HexagramDetailModal componnet.
Febuary 17 2018 | 11:19 | 12:30 | 1:11 | Improving the profermence.
| 14:30 | 17:20 | 2:50 | Improving the profermence.
| 20:00 | 22:30 | 2:30 | Improving the profermence.
Febuary 18 2018 | 11:00 | 12:40 | 1:40 | Improving the profermence. Reduced images' size.
| 13:50 | 17:30 | 3:40 | Improving the profermence. Cleared and maked css files loading asynchronous.
| 21:00 | 22:48 | 1:48 | Improving the profermence. Switched to http2
Febuary 19 2018 | 13:49 | 17:58 | 4:09 | Fixed some bugs that include hexagram detail modal display incorrectly on the small mobile screen, etc.
| 20:37 | 24:00 | 3:23 | Trying to implement code splitting with react-loadable labaary
Febuary 20 2018 | 0:00 | 1:11 | 1:11 | Trying to implement code splitting with react-loadable labaary
| 11:00 | 12:40 | 1:40 | Researching customizing name for the chunk bundles.
| 15:25 | 18:00 | 2:35 | Solved some new adjustment requests.
| 21:00 | 23:58 | 2:58 | Changed dynamic import library from react-loadable to react-imported-component inorder to use react-hot-loader in the development enviroment.
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00